## Sheet1
Defect Depletion Curve Example
Size in KLOC | 2 |  |  |  | Recidivism Rate |  | 0.2
Dev Stage | Req | Ana | HLD | LLD | Code | Unit Test | Integ Test | System Test | User
Injected | 2 | 6 | 12 | 40 | 60 | 2.5108 | 2.2849 | 1.4852
Cumulative | 2 | 8 | 20 | 60 | 120 | 122.5108 | 124.7957 | 126.2809
Est Removed | 1.2 | 3.4 | 9.24 | 27.696 | 47.0784 | 13.5586 | 12.5668 | 8.1684
Est Cumul Remvd | 1.2 | 4.6 | 13.84 | 41.536 | 88.6144 | 102.173 | 114.7398 | 122.9082
Removal Rate | 0.6 | 0.5 | 0.6 | 0.6 | 0.6 | 0.4 | 0.5 | 0.5 | ??
Residue |  | 6.8 | 15.4 | 46.16 | 78.464 | 33.8964 | 25.1336 | 16.3368
Remaining | 0.8 | 3.4 | 6.16 | 18.464 | 31.3856 | 22.8487 | 14.8517 | 9.6536
Act Removed | 1 | 4 | 8 | 30 | 40
Cumul Act Remov | 1 | 5 | 6 | 36 | 76 | 76 | 76 | 76
Cost | 2 | 2 | 2 | 2 | 2 | 6 | 16 | 35
| 2.4 | 6.8 | 18.48 | 55.392 | 94.1568 | 66.2864 | 164.5108 | 233.9137
|  |  |  | Insp Cost | 177.2288 |  | Test Cost | 464.7109
[7 empty] | Total | 641.9397
© 2001, Ed Weller, Permission to copy and duplicate is given as long as attribution is included.
Note on C2: Edward F. Weller: Put your size estimate here, whether in KLOC, FP, or other
Note on C5: Edward F. Weller: This should be the estimated injection rate per development activity through code. In test, it is an estimate based on the defective fix rate, or recidivism rate
Note on C9: Edward F. Weller: Estimated removal effectiveness per phase
Note on D10: Edward F. Weller: Injected in this phase plus remaining from last phase
Note on C14: Edward F. Weller: If you want to do a cost scenario, put in your numbers here for defect removal per phase
Note on I2: Edward F. Weller: your estimate of the percentage of bad fixes
Note on K9: Edward F. Weller: Users do not find them all, but you should assume they find at least 2/3 of the remaining defects (based on work by Ed Adams at IBM